## Compiled
Marie Adelaide Leprosy Centre, Karachi
ZERO Leprosy Project - Karachi
Target / Achievement Sheet - 2025
Activity |  |  | Jan | Feb | Mar | 1st Qtr. | Apr | May | Jun | 2nd Qtr. | Jul | Aug | Sep | 3rd Qtr. | Oct | Nov | Dec | 4th Qtr. | Grand Total
1.1.1 | Screening of all contacts (on average 50) of registered cases for leprosy and SDR-PEP eligibility. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2529 | 2529 | 2542 | 7600 | 2529 | 2529 | 2542 | 7600 | 15200
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946 | 1822 | 1535 | 5303 | 2373 | 2644 | 2619 | 7636 | 12939
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 76.95% | 72.04% | 60.39% | 69.78% | 93.83% | 104.5% | 103% | 100.5% | 85.12%
1.1.1a | Conduct house to house visit for screening and SDR PEP eligibility for household contacts | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47 | 58 | 152 | 47 | 47 | 58 | 152 | 304
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 99 | 98 | 303 | 147 | 160 | 145 | 452 | 755
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 225.5% | 210.6% | 169% | 199.3% | 312.8% | 340.4% | 250% | 297.4% | 248.4%
1.1.1b | Conduct skin-camps for screening and SDR-PEP eligibility in *hotspot. *(child case, Grade 2 Disability and more than 1 case diagnosed in last 3 years) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 10 | 10 | 16
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 1 | 10 | 4 | 1 | 1 | 6 | 16
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 166.7% | 0% | 0% | 10% | 60% | 100%
1.1.1c | Conduct field clinics for screening of leprosy and SDR-PEP eligibility in the vicinity of registered cases | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 34 | 45 | 112 | 34 | 34 | 45 | 113 | 225
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.3333 | 33 | 32.6667 | 101 | 49 | 53.3333 | 48.3333 | 150.6667 | 251.6667
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 107.1% | 97.06% | 72.59% | 90.18% | 144.1% | 156.9% | 107.4% | 133.3% | 111.9%
1.1.1d | Conduct Mobile screening clinics in peri-urban areas of Karachi | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 12 | 4 | 4 | 5 | 13 | 25
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1e | Household, Neighbours and Social contacts assessed through self screening methods (20% of the total) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 503 | 514 | 1520 | 503 | 503 | 514 | 1520 | 3040
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.2 | Regular follow-up of all under surviellence cases for Screening of their contacts | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 829 | 2459 | 815 | 815 | 837 | 2467 | 4926
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 146 | 25 | 316 | 208 | 145 | 352 | 705 | 1021
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.79% | 17.91% | 3.016% | 12.85% | 25.52% | 17.79% | 42.05% | 28.58% | 20.73%
1.1.3 | Confirmation of diagnosis of all new leprosy cases including children by senior leprosy worker. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 4 | 9 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 2 | 11 | 5 | 1 | 7 | 13 | 24
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 220% | 0% | 25% | 77.78% | 100% | 133.3%
1.1.4 | Calculate and procure/secure Rifampicin with 10% buffer stock. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004 | 2002 | 2002 | 6008 | 2002 | 2002 | 2002 | 6006 | 12014
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004 | 2002 | 2002 | 6008 | 2002 | 2002 | 2002 | 6006 | 12014
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.5 | Printing of relevant forms & stationary (consent, contact list, SDR-PEP card) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004 | 2002 | 2002 | 6008 | 2002 | 2002 | 2002 | 6006 | 12014
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004 | 2002 | 2002 | 6008 | 2002 | 2002 | 2002 | 6006 | 12014
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.1.6 | Administer SDR-PEP to eligible contacts after consent. (# of contacts) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1720 | 1720 | 1732 | 5172 | 1720 | 1720 | 1738 | 5178 | 10350
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781 | 653 | 425 | 1859 | 1089 | 1332 | 1492 | 3913 | 5772
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45.41% | 37.97% | 24.54% | 35.94% | 63.31% | 77.44% | 85.85% | 75.57% | 55.77%
1.1.7 | Follow-up of contacts who refused SDR-PEP or who were not eligible at initial visit. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 330 | 342 | 1002 | 330 | 330 | 349 | 1009 | 2011
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 357 | 168 | 0 | 0 | 168 | 525
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 104.4% | 35.63% | 50.91% | 0% | 0% | 16.65% | 26.11%
1.2.1 | Conduct leprosy trainings for dermatologist (students and fully-trained) and general practioners. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 100 | 200
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 78 | 72 | 5 | 155 | 205
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 78% | 0% | 0% | 155% | 102.5%
1.2.2 | Conduct leprosy trainings for under-graduate students of medicine. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.3 | Conduct leprosy trainings for lady health workers. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 4
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 3 | 0 | 3 | 5
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 150% | 0% | 150% | 125%
1.2.4 | Conduct leprosy orientation for nursing staff and nursing students. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 3
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 3
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 100% | 100%
1.2.5 | Conduct leprosy orientation for traditional and faith healers. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 10 | 20
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 6 | 0 | 6 | 14
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 80% | 0% | 60% | 0% | 60% | 70%
1.2.6 | Conduct leprosy orientation for pharmacists, dispensers, compounders, and pharmacy staff. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100%
1.2.7 | Conduct awareness sessions in educational institutions . (# of schools, # Colleges, # Universities) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 8
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 8
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100%
1.2.8 | Conduct one-week training courses/refresher trainings on Leprosy/TB for senior paramedical workers | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.9 | Conduct one-year basic Training Course (Leprosy/TB) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.10 | Conduct customized short leprosy trainings for paramedical workers. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.1.1 | Conduct Out Patients consultations through clinics for other common Skin Conditions | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838 | 1838 | 1850 | 5526 | 1838 | 1838 | 1854 | 5530 | 11056
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072 | 2596 | 2775 | 8443 | 2476 | 2325 | 2349 | 7150 | 15593
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 167.1% | 141.2% | 150% | 152.8% | 134.7% | 126.5% | 126.7% | 129.3% | 141%
2.1.2 | To conduct Skin Smear Microscopy of Leprosy Presumptive cases for confirmation of diagnosis, and follow-up of treatment | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 7 | 15 | 22 | 36
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12 | 4 | 22 | 10 | 2 | 14 | 26 | 48
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28.57% | 157.1% | 0% | 28.57% | 93.33% | 118.2% | 133.3%
2.1.3 | To provide all Leprosy patients appropriate and adequate treatment as per WHO guidelines | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 3 | 10 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 2 | 11 | 5 | 1 | 7 | 13 | 24
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 220% | 0% | 33.33% | 70% | 100% | 133.3%
2.1.4 | To follow-up all Leprosy patients for drug compliance and disease outcome | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 3 | 10 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 2 | 11 | 5 | 1 | 7 | 13 | 24
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 220% | 0% | 33.33% | 70% | 100% | 133.3%
2.1.5 | Treatment provided for patients with other common Skin Conditions | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838 | 1838 | 1850 | 5526 | 1838 | 1838 | 1854 | 5530 | 11056
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3072 | 2596 | 2775 | 8443 | 2476 | 2325 | 2349 | 7150 | 15593
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 167.1% | 141.2% | 150% | 152.8% | 134.7% | 126.5% | 126.7% | 129.3% | 141%
2.2.1 | Follow-up patients under surveillance for early diagnosis and management of disease-related complications | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 28 | 43 | 97 | 26 | 29 | 47 | 102 | 199
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 7 | 18 | 12 | 9 | 18 | 39 | 57
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.08% | 17.86% | 16.28% | 18.56% | 46.15% | 31.03% | 38.3% | 38.24% | 28.64%
2.2.2 | Admit patients in wards for early management of reactions, neuritis and ulcers | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.2.3 | Re-enforcement of leprosy workers for timely detection and management of complications | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 1 | 0 | 0 | 1 | 5
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 1 | 0 | 0 | 1 | 5
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100%
2.3.1 | Provide assistive devices/mobility-aid to patients as per need | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 9 | 9 | 14
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 2 | 12 | 4 | 8 | 4 | 16 | 28
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 240% | 0% | 0% | 44.44% | 177.8% | 200%
2.3.2 | Provide protective footwear to patients as per need | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 17 | 40 | 11 | 12 | 20 | 43 | 83
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 7 | 15 | 33 | 10 | 5 | 17 | 32 | 65
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 58.33% | 88.24% | 82.5% | 90.91% | 41.67% | 85% | 74.42% | 78.31%
2.3.3 | Provide physiotherapy services to patients as per need. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2 | 8 | 23 | 14 | 20 | 11 | 45 | 68
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.3.4 | Train all new patients on self care methods | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 13 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 2 | 11 | 5 | 1 | 7 | 13 | 24
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 220% | 0% | 0% | 53.85% | 100% | 133.3%
2.4.1 | Conduct mental health assessment through OPDs | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 16 | 17 | 50 | 16 | 17 | 17 | 50 | 100
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 47 | 15 | 111 | 111
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 306.2% | 276.5% | 88.24% | 222% | 111%
2.4.2 | Provision of counselling sessions by trained psychologist | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 14 | 44 | 15 | 14 | 15 | 44 | 88
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 34 | 25 | 90 | 90
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 206.7% | 242.9% | 166.7% | 204.5% | 102.3%
2.4.3 | Referral of patients showing moderate to severe symptoms for psychiatric evaluation | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 7 | 2 | 2 | 2 | 6 | 13
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 2 | 0 | 3 | 5
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 50% | 28.57% | 50% | 100% | 0% | 50% | 38.46%
2.4.4 | Sensitization of Leprosy workers, family/community members on mental health | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 34 | 100 | 33 | 34 | 33 | 100 | 200
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 98 | 206 | 206
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 317.6% | 297% | 206% | 103%
2.4.5 | Provide vocational skills / * Income Generation for patients | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 9 | 9 | 14
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 11
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 122.2% | 122.2% | 78.57%
2.4.6 | Establish linkage with available social protection schemes | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 9 | 9 | 14
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 166.7% | 166.7% | 107.1%
2.4.7 | Provide residential care for people affected by Leprosy without family support | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 21
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 14
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 66.67% | 66.67%
2.5.1 | Include people affected by leprosy in awareness campaign. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 4 | 5
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2 | 3
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 50% | 0% | 50% | 60%
2.5.2 | Develop / Printing of IEC material on Leprosy/Skin NTDs. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.3 | Increase awareness about leprosy/Skin-NTDs among patients, family members and their communities. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836 | 836 | 836 | 2508 | 836 | 836 | 843 | 2515 | 5023
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3361 | 2661 | 2359 | 8381 | 2442 | 12504 | 2483 | 17429 | 25810
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 402% | 318.3% | 282.2% | 334.2% | 292.1% | 1496% | 294.5% | 693% | 513.8%
2.5.4 | Awareness events to sensitize community for stigma reduction and inclusion of person affected by Leprosy | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 27 | 27
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 900% | 900%
2.5.5 | Develop informative short videos / Success stories for public awareness. (# of videos) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.6 | Develop and upload social posts and videos on social media platforms for leprosy awareness. (# of social posts) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.7 | Enrolment of people affected by Leprosy in organizations of persons with disabilities. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.8 | Lobbying to repeal/amend existing discriminatory laws against people affected by leprosy. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.1.1 | Established centre to provide Leprosy knowledge/skills in post elimination phase (Competence centre) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.1.2 | Establish network/partnership with Dermatologists/GPs for referral system | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 9 | 10 | 10
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 1 | 0 | 5 | 6 | 10
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 55.56% | 60% | 100%
3.1.3 | To provide timely feedback and acknowledgement to referring dermatologist/GPs for their support | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 4 | 1 | 0 | 5 | 6 | 10
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 120% | 200%
3.2.1 | Continue patients mapping in Karachi & interior Sindh to achieve 90% coverage by 2027 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 300 | 100 | 100 | 100 | 300 | 600
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 89 | 88 | 267 | 114 | 99 | 104 | 317 | 584
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 89% | 88% | 89% | 114% | 99% | 104% | 105.7% | 97.33%
3.2.2 | Initiate patients mapping in 2025 in other provinces (Baluchistan, KPK, Azad Kashmir & Gilgit Baltistan) and 90% coverage by 2028 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.3 | Start Implementation of Kobo Collect for patient mapping, contact screening and SDR-PEP. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
3.2.4 | Develop digital database on DHIS2 for digitalization of leprosy data. (HR +3, Software, Server, Gadget, internet) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.5 | Establish reliable processes to enable digital data management. (who is collecting the data, who is entering the data, infrastructure etc) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.6 | Conduct trainings for project staff on digital data management system (DHIS2, Kobo Collect, QGIS). --->TOT (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.7 | Conduct trainings for field staff. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.1 | Training on sample collection of Skin Biopsy, new diagnostic tools along with its execution. (organizational learning/TOT) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.2 | Training on sample collection of Skin Biopsy, new diagnostic tools along with its execution. (Field Staff) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.3 | Collect, store and send samples to ALP based on SOPs developed by ITM. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 13 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.4 | Inform patients about biopsy results. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 13 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.5 | Conduct Quantitative Polymerase Chain Reaction (qPCR) test for people with unclear leprosy presentations. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 13 | 13 | 18
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.1 | Centres' staff Participate in the quarterly meetings arranged by provincial/regional TB Control Program. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 4
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 2 | 2 | 8
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 300% | 300% | 0% | 0% | 100% | 100% | 200%
4.1.2 | Screening of TB Contacts of all B+ve patients registered during the year through house visits / OPD | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 247 | 249 | 255 | 751 | 249 | 249 | 257 | 755 | 1506
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 549 | 0 | 0 | 522 | 522 | 1071
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 215.3% | 73.1% | 0% | 0% | 203.1% | 69.14% | 71.12%
4.1.3 | Conduct Chest Camps in endemic areas for TB | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 7 | 8 | 9
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 4 | 2 | 1 | 2 | 5 | 9
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 0% | 0% | 400% | 200% | 0% | 28.57% | 62.5% | 100%
4.1.4 | Conduct out Patients consultation through clinics for TB | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092 | 2092 | 2095 | 6279 | 2092 | 2093 | 2098 | 6283 | 12562
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6260 | 6260 | 0 | 0 | 7810 | 7810 | 14070
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 298.8% | 99.7% | 0% | 0% | 372.3% | 124.3% | 112%
4.1.5 | To conduct Sputum Smear Microscopy/GeneXpert for diagnosis of all new TB presumptive / cases | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 571 | 578 | 1720 | 571 | 574 | 578 | 1723 | 3443
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742 | 742 | 0 | 0 | 877 | 877 | 1619
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 128.4% | 43.14% | 0% | 0% | 151.7% | 50.9% | 47.02%
4.1.6 | To provide all TB patients appropriate and adequate treatment as per WHO guidelines | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 123 | 131 | 375 | 123 | 123 | 133 | 379 | 754
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 341 | 0 | 0 | 385 | 385 | 726
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 260.3% | 90.93% | 0% | 0% | 289.5% | 101.6% | 96.29%
4.1.7 | To follow-up all TB patients for drug compliance and disease outcome | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 123 | 131 | 375 | 123 | 123 | 133 | 379 | 754
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 341 | 0 | 0 | 385 | 385 | 726
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 260.3% | 90.93% | 0% | 0% | 289.5% | 101.6% | 96.29%
4.1.8 | To Identify and Refer DR TB to PMDT site for further management | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 5 | 1 | 2 | 2 | 5 | 10
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 20% | 0% | 0% | 50% | 20% | 20%
5.1.1 | Inception workshop to kick-off the project and set-up M&E system. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.2 | Conduct trainings for project workers on zero-leprosy implementation and planning of targets. (# of participants) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.3 | Regular entry of data collected from centres | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.4 | Generation of regular reports for learning and onward submissions | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
5.1.6 | Conduct quarterly meetings of Provincial Project team. (# of meetings) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 2
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100%
5.1.7 | Conduct bi-annual meeting of Project team (Medical, Admin & Finance) at HQ / MALC. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.8 | Monitoring visits to leprosy centres on a regular basis. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
5.1.9 | Conduct mid-term evaluation. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.10 | Conduct end-term evaluation. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.11 | Implement Webmo tool for monitoring and evaluation. (MEAL Officer, Data Entry Operator) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.12 | Implementation of operational research ((e.g. cost effectiveness of active case finding activities, qualitative research on GD2, stigma, delay of diagnosis) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.13 | Publication of operation research | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.14 | Dissemination of results (Annual Project Progress report) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.15 | Strategic workshops to disseminate lessons learned from both experiences (Team Togo + Team Pakistan) | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.16 | Annual audits. | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | % | 0% | 0% | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%