## HQ_TR_HE_HOSP
Marie Adelaide Leprosy Centre, Karachi
ZERO Leprosy Project - Karachi
Target / Achievement Sheet - 2025
Activity |  |  | Jan | Feb | Mar | 1st Qtr. | Apr | May | Jun | 2nd Qtr. | Jul | Aug | Sep | 3rd Qtr. | Oct | Nov | Dec | 4th Qtr. | Grand Total
1.1.1 | Screening of all contacts (on average 50) of registered cases for leprosy and SDR-PEP eligibility. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1a | Conduct house to house visit for screening and SDR PEP eligibility for household contacts | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1b | Conduct skin-camps for screening and SDR-PEP eligibility in *hotspot. *(child case, Grade 2 Disability and more than 1 case diagnosed in last 3 years) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1c | Conduct field clinics for screening of leprosy and SDR-PEP eligibility in the vicinity of registered cases | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1d | Conduct Mobile screening clinics in peri-urban areas of Karachi | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.1e | Household, Neighbours and Social contacts assessed through self screening methods (20% of the total) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.2 | Regular follow-up of all under surviellence cases for Screening of their contacts | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.3 | Confirmation of diagnosis of all new leprosy cases including children by senior leprosy worker. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.4 | Calculate and procure/secure Rifampicin with 10% buffer stock. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.5 | Printing of relevant forms & stationary (consent, contact list, SDR-PEP card) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.6 | Administer SDR-PEP to eligible contacts after consent. (# of contacts) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.1.7 | Follow-up of contacts who refused SDR-PEP or who were not eligible at initial visit. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.1 | Conduct leprosy trainings for dermatologist (students and fully-trained) and general practioners. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.2 | Conduct leprosy trainings for under-graduate students of medicine. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 | 12.5 | 12.5 | 12.5 | 37.5 | 12.5 | 12.5 | 12.5 | 37.5 | 75
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  | 54 | 54 | 12 | 8 | 6 | 26 | 80
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 432% | 144% | 96% | 64% | 48% | 69.33% | 106.7%
1.2.3 | Conduct leprosy trainings for lady health workers. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.4 | Conduct leprosy orientation for nursing staff and nursing students. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.5 | Conduct leprosy orientation for traditional and faith healers. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.6 | Conduct leprosy orientation for pharmacists, dispensers, compounders, and pharmacy staff. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.7 | Conduct awareness sessions in educational institutions . (# of schools, # Colleges, # Universities) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.2.8 | Conduct one-week training courses/refresher trainings on Leprosy/TB for senior paramedical workers | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
1.2.9 | Conduct one-year basic Training Course (Leprosy/TB) | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
1.2.10 | Conduct customized short leprosy trainings for paramedical workers. | Planned |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 | 2
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 | 2
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | 100%
2.1.1 | Conduct Out Patients consultations through clinics for other common Skin Conditions | Planned |  |  |  | 0 |  |  |  | 0 | 1167 | 1167 | 1167 | 3501 | 1167 | 1166 | 1166 | 3499 | 7000
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 2206 | 1302 | 1564 | 5072 | 1267 | 1082 | 1001 | 3350 | 8422
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 189% | 111.6% | 134% | 144.9% | 108.6% | 92.8% | 85.85% | 95.74% | 120.3%
2.1.2 | To conduct Skin Smear Microscopy of Leprosy Presumptive cases for confirmation of diagnosis, and follow-up of treatment | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.1.3 | To provide all Leprosy patients appropriate and adequate treatment as per WHO guidelines | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.1.4 | To follow-up all Leprosy patients for drug compliance and disease outcome | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.1.5 | Treatment provided for patients with other common Skin Conditions | Planned |  |  |  | 0 |  |  |  | 0 | 1167 | 1167 | 1167 | 3501 | 1167 | 1166 | 1166 | 3499 | 7000
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 2206 | 1302 | 1564 | 5072 | 1267 | 1082 | 1001 | 3350 | 8422
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 189% | 111.6% | 134% | 144.9% | 108.6% | 92.8% | 85.85% | 95.74% | 120.3%
2.2.1 | Follow-up patients under surveillance for early diagnosis and management of disease-related complications | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.2.2 | Admit patients in wards for early management of reactions, neuritis and ulcers | Planned |  |  |  | 0 |  |  |  | 0 | 33 | 34 | 33 | 100 | 33 | 34 | 33 | 100 | 200
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 48 | 30 | 37 | 115 | 26 | 22 | 33 | 81 | 196
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 145.5% | 88.24% | 112.1% | 115% | 78.79% | 64.71% | 100% | 81% | 98%
2.2.3 | Re-enforcement of leprosy workers for timely detection and management of complications | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 2 | 1 | 3 | 3
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 2 | 1 | 3 | 3
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
2.3.1 | Provide assistive devices/mobility-aid to patients as per need | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.3.2 | Provide protective footwear to patients as per need | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.3.3 | Provide physiotherapy services to patients as per need. | Planned |  |  |  | 0 |  |  |  | 0 | 8 | 8 | 9 | 25 | 8 | 8 | 9 | 25 | 50
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.3.4 | Train all new patients on self care methods | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.1 | Conduct mental health assessment through OPDs | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.2 | Provision of counselling sessions by trained psychologist | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.3 | Referral of patients showing moderate to severe symptoms for psychiatric evaluation | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.4 | Sensitization of Leprosy workers, family/community members on mental health | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.5 | Provide vocational skills / * Income Generation for patients | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.6 | Establish linkage with available social protection schemes | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.4.7 | Provide residential care for people affected by Leprosy without family support | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.1 | Include people affected by leprosy in awareness campaign. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.2 | Develop / Printing of IEC material on Leprosy/Skin NTDs. | Planned |  |  |  | 0 |  |  |  | 0 | 50000 |  |  | 50000 |  |  |  | 0 | 50000
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 50000 |  |  | 50000 |  |  |  | 0 | 50000
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
2.5.3 | Increase awareness about leprosy/Skin-NTDs among patients, family members and their communities. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.4 | Awareness events to sensitize community for stigma reduction and inclusion of person affected by Leprosy | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.5 | Develop informative short videos / Success stories for public awareness. (# of videos) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 100%
2.5.6 | Develop and upload social posts and videos on social media platforms for leprosy awareness. (# of social posts) | Planned |  |  |  | 0 |  |  |  | 0 | 4 | 4 | 4 | 12 | 4 | 5 | 5 | 14 | 26
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 4 | 4 | 4 | 12 | 4 | 5 | 5 | 14 | 26
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.5.7 | Enrolment of people affected by Leprosy in organizations of persons with disabilities. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2.5.8 | Lobbying to repeal/amend existing discriminatory laws against people affected by leprosy. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 1 |  | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 100%
3.1.1 | Established centre to provide Leprosy knowledge/skills in post elimination phase (Competence centre) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.1.2 | Establish network/partnership with Dermatologists/GPs for referral system | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.1.3 | To provide timely feedback and acknowledgement to referring dermatologist/GPs for their support | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.1 | Continue patients mapping in Karachi & interior Sindh to achieve 90% coverage by 2027 | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.2 | Initiate patients mapping in 2026 in other provinces (Baluchistan, KPK, Azad Kashmir & Gilgit Baltistan) and 90% coverage by 2028 | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.3 | Start Implementation of Kobo Collect for patient mapping, contact screening and SDR-PEP. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.4 | Develop digital database on DHIS2 for digitalization of leprosy data. (HR +3, Software, Server, Gadget, internet) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.2.5 | Establish reliable processes to enable digital data management. (who is collecting the data, who is entering the data, infrastructure etc) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
3.2.6 | Conduct trainings for project staff on digital data management system (DHIS2, Kobo Collect, QGIS). --->TOT (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 | 1 |  |  | 1 | 2
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 | 1 |  |  | 1 | 2
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100%
3.2.7 | Conduct trainings for field staff. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 6
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 6
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3.3.1 | Training on sample collection of Skin Biopsy, new diagnostic tools along with its execution. (organizational learning/TOT) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 2 | 2 | 2
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.2 | Training on sample collection of Skin Biopsy, new diagnostic tools along with its execution. (Field Staff) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 6 | 6 | 6
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.3 | Collect, store and send samples to ALP based on SOPs developed by ITM. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.4 | Inform patients about biopsy results. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3.3.5 | Conduct Quantitative Polymerase Chain Reaction (qPCR) test for people with unclear leprosy presentations. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.1 | Centres' staff Participate in the quarterly meetings arranged by provincial/regional TB Control Program. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.2 | Screening of TB Contacts of all B+ve patients registered during the year through house visits / OPD | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.3 | Conduct Chest Camps in endemic areas for TB | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.4 | Conduct out Patients consultation through clinics for TB | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.5 | To conduct Sputum Smear Microscopy/GeneXpert for diagnosis of all new TB presumptive / cases | Planned |  |  |  | 0 |  |  |  | 0 | 1000 | 1000 | 1000 | 3000 | 1000 | 1000 | 1000 | 3000 | 6000
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 6 | 6 | 341 | 353 | 113 | 144 | 151 | 408 | 761
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.6% | 0.6% | 34.1% | 11.77% | 11.3% | 14.4% | 15.1% | 13.6% | 12.68%
4.1.6 | To provide all TB patients appropriate and adequate treatment as per WHO guidelines | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.7 | To follow-up all TB patients for drug compliance and disease outcome | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4.1.8 | To Identify and Refer DR TB to PMDT site for further management | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.1 | Inception workshop to kick-off the project and set-up M&E system. | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.2 | Conduct trainings for project workers on zero-leprosy implementation and planning of targets. (# of participants) | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.3 | Regular entry of data collected from centres | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.4 | Generation of regular reports for learning and onward submissions | Planned |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 | 1 |  |  | 1 |  |  |  | 0 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
5.1.6 | Conduct quarterly meetings of Provincial Project team. (# of meetings) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.7 | Conduct bi-annual meeting of Project team (Medical, Admin & Finance) at HQ / MALC. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
5.1.8 | Monitoring visits to leprosy centres on a regular basis. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.9 | Conduct mid-term evaluation. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.10 | Conduct end-term evaluation. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.11 | Implement Webmo tool for monitoring and evaluation. (MEAL Officer, Data Entry Operator) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 1 | 1
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
5.1.12 | Implementation of operational research ((e.g. cost effectiveness of active case finding activities, qualitative research on GD2, stigma, delay of diagnosis) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.13 | Publication of operation research | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.14 | Dissemination of results (Annual Project Progress report) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.15 | Strategic workshops to disseminate lessons learned from both experiences (Team Togo + Team Pakistan) | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
5.1.16 | Annual audits. | Planned |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | Achieved |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
|  | % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%